## Sheet1
Number | Bug Description | Date Found | Repro Steps (if Applicable) | Notes | Likely bug location | Date Fixed | Fixed By
1 | Scrolling on main screen does not work | 2012-11-12 | Try to scroll on the main screen after visiting a RIdeDetails page |  | ListofRides.java | 2012-11-13 | Vinai
2 | Top Thrill Dragster ride has description for Millenium Force | 2012-11-15 | Navigate to Top Thrill Dragster page |  | XML file for TTD | 2012-11-20 | Eric
3 | Map is centered on the wrong screen | 2012-11-16 | Go to the map page on a high-res device or emulator |  | DisplayMap.java | 2012-11-18 | Tom
4 | Unclicking a ride does not remove it from the list | 2012-11-17 | Check a ride and then uncheck. The checkbox is undone but it is still stored internally in the list of RIdes. |  | ListofRides.java | 2012-11-19 | Vinai
5 | Some rides don't link to description page | 2012-11-30 |  | Matterhorn, Millenium, Maverick are empty | XML files incomplete | 2012-12-01 | Eric
6 | Coordinates for some rides were incorrect | 2012-12-01 |  | Re-assign some coordinates in the XML files | XML | 2012-12-02 | Tom
7 | Route didn't include some rides | 2012-12-03 | Try routing various paths, including those going through both the top and right sections | Most paths work | RidePath.java | 2012-12-03 | Aaron
8 | Millenium Force Youtube link was incorrect | 2012-12-03 | Open the Millenium Force youtube link. |  | XML file | 2012-12-03 | Vinai
9 | Text labels do not display legibly on large displays | 2012-12-05 | Open the map on a high resolution display or emulator and look at the size of the text labels |  | MapCanvas.java | 2012-12-05 | Tom
10 | Unclicking a ride does not remove it from the list | 2012-12-05 | Check a ride and then uncheck. Route map. | This is a regression of Number 4 | ListofRides.java | 2012-12-05 | Eric
11 | Clicking the Mantis button (or the map node) crashes the app | 2012-12-06 | Just press the Mantis button on the ListofRides page. May also happen when pushing the map node for Mantis. | Completely crashes app. Works fine if you do not navigate to RideDetails page for Mantis | Mantis XML |  | Eric
12 | Routes through the right subsection of the ride do not route properly | 2012-12-06 | Check a ride in the right subsection of the park (and any other rides). | Check the routing algorithm dealing with the right subsection. | RidePath.java | 2012-12-07 | Eric
13 | App crashes when routing through Jr. Gemini | 2012-12-06 | Try to use Jr. Gemini as part of a route | Check spelling of Jr. vs Junior | RidePath / XML / Ride | 2012-12-07
14 | Some pictures of rides don't show up on high-res devices | 2012-12-04 | Run application on a high-res device and open a ride with a high resolution image (Matterhorn, Millenium, etc.) | May deal with scaling the bitmap and screen coordinate conversion | RideDetails.java | 2012-12-07 | Vinai